Kenya High School Alumnae Society — Careers & Mentorship Programme

WG2 (Mentors) — Boma Career Day 2026 Coordination & Delivery Plan

# WG2 (Mentors) — Boma Career Day 2026 Coordination & Delivery Plan

Prepared for: Cizarina Nasirumbi and Margaret Ogachi, WG2 Assistant Leads Prepared: 5 August 2026 | Last updated: 17 August 2026 | Career Day: Saturday, 29 August 2026 | Days remaining: 12 Source: KHSAS CMP SteerCo Action Log, Meeting 1/2026 (24 Jul 2026, V1 updated 04 Aug 2026); WG2 2023 Mentor Clusters (carried forward and refined for 2026); the WG2 App's own schedule data (15 Aug 2026, Revision 3) — now the authoritative source for Section 18

What changed in this update: Section 18 (Event Day Master Schedule) is fully rewritten to match the schedule the WG2 App actually runs on (Revision 3, locked 15 Aug) — the day starts later (10:45am mentorship start, not 07:00am) and WG2 has zero role in the Opening/Closing Plenary, which is entirely WG4's and isn't modelled anywhere in this Playbook. Also updated: Section 6 (RACI) gains a Room & AV Setup row; Section 8.5 now matches the real 3-cohort model; Section 9 notes the Mentor Database's secondary-cluster field; Sections 12 and 14 point to two new companion documents that supersede their draft outlines; Section 15's WG4 relationship is clarified. See Section 20 (new) for the full companion document list, including the WG2 App's live Reports and Dashboard views, which now supersede static recruitment targets as the source of truth for current mentor coverage.

## 1. Why WG2 Is the Heart of Career Day

Three resolutions from the SteerCo make WG2's mandate explicit:

| Ref | Resolution | Owner |
| --- | --- | --- |
| R04 | The two-cohort staggered delivery model was adopted. | Secretariat, WG2, WG8 |
| R05 | The programme will allocate more time to learner mentorship than to the plenary. | Secretariat |
| R06 | KICD and KUCCPS experts will be engaged for cohort-specific labs, not the main plenary. | WG2, WG8 |
| R08 | Mentor feedback will be collected after the event. | WG2 |

Every other Working Group builds the container (logistics, finance, comms, booths, plenary). WG2 builds what students will actually remember. If mentorship is weak, Career Day fails regardless of how well everything else runs.

## 2. WG2 Scope of Work (Standing Mandate)

Design and deliver the mentorship experience — assign mentors, organize clusters, ensure every cluster has leadership, structure the discussions, brief mentors, and send learners away with practical guidance.

Build the mentorship cluster structure — clusters, leads, sub-leads, mentor assignment, student assignment, communication channels (Action A17).

Recruit and coordinate mentors — sufficient numbers, confirmations, attendance, replacements, briefing, follow-up.

Coordinate KICD and KUCCPS experts into cohort-specific labs (Action A19, with WG8).

Protect mentorship time in the programme — push back on speeches (Action A20, with Secretariat, WG4, WG8).

Develop the mentor feedback tool (Action A21).

Support student routing — how learners move between opening, mentorship, labs, booths, plenary, closing (Action A31, with WG8).

Integrate teachers and the Chaplain into the working structure (Action A32, with WG8, Secretariat).

### 2.1 Official WG2 Duties (per WG2 Group Description)

This is the standing duty list published in the WG2 group description — the day-to-day breakdown behind the mandate above. Where a duty is already tracked elsewhere in this Playbook, that's noted; a few are new and now added as tasks in the WG2 App.

Organise training of Cluster Leads & Sub-Leads & all available Mentors — folded into the Mentor Briefing Session (Section 13), now explicitly scoped to cover Cluster Lead/Sub-Lead responsibilities as well as general mentor prep.

Maintain a database of, and liaise with, Cluster Leads — the Mentor Database (Section 9) already carries Cluster Lead/Sub-Lead as a role field; Zone Coordinators are the liaison layer (Section 8.2).

Have Leads send confirmed attending-mentor numbers 10 days pre-event — new deadline; added as a task in the WG2 App (~19 Aug, 10 days before 29 Aug).

Keep clusters informed & respond to queries — ongoing, carried by Zone Coordinators and the Cluster Leads chat (Section 8.6, Action A18).

Direct diaspora queries in the clusters to the Diaspora Liaison — new: WG2 needs to confirm who holds the Diaspora Liaison role (likely a Secretariat or WG3 contact) and share it with all Zone Coordinators/Cluster Leads so queries get routed correctly. Flagged as an open item until that contact is named.

Prepare all mentor-related documents (Mentors' Brief, Site Plan, cluster room labels, Mentors' Feedback Form, Students' Feedback Form) and ensure they reach the clusters — the Mentor Feedback Form is covered (Section 11); the Mentors' Brief, Site Plan, cluster room labels, and a separate Students' Feedback Form are new build tasks, tracked in the WG2 App.

Co-ordinate with the School WG (WG8) on the post-mentorship Networking Tea — new coordination item, tracked in the WG2 App.

Mentorship Session co-ordination with WG8 — room availability & allocation (already covered under the Zone Model, Section 8, and the Master Schedule, Section 18); on-the-ground student support — ushers/marshals, registration desk (extends the marshal/entrance-staffing plan in Section 19.5); posting A3/Site Plan copies on school notice boards (new, tracked in the WG2 App).

Post-event reports — covered by the Post-Event Impact Report (Section 16).

## 3. Current WG2 Structure (per Action Log, as at 4 Aug 2026)

| Role | Name |
| --- | --- |
| Lead | Dr Muthoni Mugambi (Faith) (2018) |
| Assistant Leads (two) | Cizarina Nasirumbi (1999) and Margaret Ogachi (2015) — confirmed 6 Aug; see Section 8.2 for how oversight splits between them |
| Interns | Elsie Munge, Lena Wekunda, Abigail Amanda Adika, Keisha Wahome, Jeddy Kolil, Seanice Ochieng, Sarah Bora |
| Members | Anne Obure, Gloria Kikete (Society Secretary-General), Hannah Gitonga, Tamara Ariba, Lorraine Muturi, Wangechi Ndirangu, Mercy Amuguni, Sharon Chachale-Wata |
| Unconfirmed (chase via straw poll, deadline 7 Aug 10am) | June Kyula, Agnes Maina-Gwaro, Annabel Njoroge, Jane Gachanja, Mary Mugambi, Sylvia Wanjie-Muniu, Tabitha Waithaka |

Straw Poll: https://strawpoll.com/GPgVYGlzzna (closes 07 Aug, 10:00 EAT) WG2 WhatsApp: https://chat.whatsapp.com/E4rZAKUHA218OyeKzCYVUb WG2 Drive folder: https://drive.google.com/drive/folders/1DhiMUEeSuAU7IC5aGLmXlISLip6e3Aql

Action needed this week: flag to Secretariat that WG2 has two confirmed Assistant Leads (Action A13/A15 should reflect this, not the old "TBC" note), and follow up every unconfirmed member individually — a "no response" by 7 Aug is treated as unavailable and they will be dropped from the chat. Five of the confirmed Members will also need to be tapped as Zone Coordinators (Section 8.6) — flag this to them now so it isn't a surprise later.

## 4. WG2's Direct Line Items in the Action Log

Updated 17 Aug 2026 from the SteerCo Meeting 2/2026 Action Log (7 Aug 2026, approved 14 Aug 2026) — this replaces the Meeting 1/2026 reference numbers (the old A13–A32 series) with WG2's own current docket (A01–A18). The Status column has been removed on purpose: a lot of this has already moved since 14 Aug, and the WG2 App's Google Sheet is the live record — a status column here would just go stale again and risk showing the wrong thing. Check the app for where each item actually stands.

| Ref | Deliverable | Due | Notes |
| --- | --- | --- | --- |
| A01 | Confirm the Working Group Lead and Assistant Lead | 14 Aug | Resolved — Dr Muthoni Mugambi (Lead); Cizarina Nasirumbi and Margaret Ogachi (both Assistant Leads) |
| A02 | Submit the WG2 budget to WG1 Finance | 11 Aug | New — not previously tracked anywhere in this Playbook. No WG2 budget line exists yet; flagged in Section 20 |
| A03 | Finalise the WG2 roster and structure | 14 Aug | See Section 3 — cross-check against the new Action Log's WG2 roster (Section 20 flags a discrepancy) |
| A04 | Finalise the WG2 checklist and 7-day workplan, upload to Drive | 14 Aug | This Playbook + Section 17 fulfils this |
| A05 | Confirm the five Zone Coordinators | 14 Aug | Section 8.6 — draft candidates named, confirm still accurate (Section 20) |
| A06 | Finalise the 23-cluster / 5-zone mentorship structure | 14 Aug | Section 7 |
| A07 | Confirm Cluster Leads, Sub-Leads and the mentorship reporting structure | 14 Aug | Section 8.2, Section 12 |
| A08 | Continue sourcing mentors, prioritising Earth Sciences/Energy/Mining (B3), Agriculture/Food/Agribusiness (B5), Supply Chain (C4), and Uniformed & National Security Services (D3) | 14 Aug | Section 7.2 tiers; check current gaps live in the app's Mentor Coverage Analysis (Section 20) |
| A09 | Validate learner interest in the Uniformed & National Security Services cluster (with WG8) | 14 Aug | Section 7.2 flags D3's interest level as an inference, not confirmed data — still open |
| A10 | Finalise the proposed student tracking system for mentorship sessions | 14 Aug | Already delivered — this is the WG2 App's QR check-in system (Section 19.2–19.3) |
| A11 | Prepare fallback arrangements for clusters where mentor numbers may be insufficient | 14 Aug | Section 7.3 fallback merges |
| A12 | Engage the KICD expert for the relevant cohort-specific lab (with WG8) | 14 Aug | Section 7.4 |
| A13 | Engage the KUCCPS expert for the relevant cohort-specific lab (with WG8) | 14 Aug | Section 7.4 |
| A14 | Confirm the rooms for the cohort-specific labs (with WG8) | 14 Aug | Section 18.7 — Old Dining Hall capacity (800–850) now confirmed by WG8, see Section 20 |
| A15 | Revise the programme to protect sufficient learner mentorship time (with CMP Directorate, WG3, WG8) | 14 Aug | Section 1 (R05) |
| A16 | Place the KICD expert within the relevant cohort lab (with CMP Directorate, WG8) | 14 Aug | Section 7.4 |
| A17 | Place the KUCCPS expert within the relevant cohort lab (with CMP Directorate, WG8) | 14 Aug | Section 7.4 |
| A18 | Prepare a concise mentor feedback tool | Before 29 Aug | Section 11 |

## 5. Three-Week Master Work Plan

### Phase 0 — Now to SteerCo Meeting 2 (Wed 5 – Fri 7 Aug) — URGENT

| Task | Owner | Due | Output |
| --- | --- | --- | --- |
| Resolve Assistant Lead: Cizarina or Margaret Ogachi | Dr Muthoni + Cizarina | 6 Aug | Confirmed to Secretariat |
| Chase all unconfirmed WG2 members for the straw poll | Cizarina + interns | 7 Aug, 10am | Confirmed roster |
| Confirm the reorganized 2026 cluster list — 23 clusters in Section 7 (a MECE reorganization of the 2023 list: overlaps resolved, gaps closed) and lock the 5-Zone structure | Dr Muthoni, Cizarina, WG2 core | 6 Aug | Confirmed cluster list + zone map |
| Appoint 5 Zone Coordinators from confirmed Members (Section 8.6) | Dr Muthoni + Cizarina | 6 Aug | Zones staffed with a coordinator each |
| Draft WG2 roster & structure doc (A15) | Cizarina | 7 Aug | Upload to WG2 Drive |
| Draft WG2 7-day workplan/checklist (A16) | Cizarina | 7 Aug | This playbook + tracker |
| Assign a WG2 liaison/Zone Coordinator to every cluster; check Cluster Lead/Sub-Lead availability (A17) | Dr Muthoni + Cizarina + Zone Coordinators | 7 Aug | Cluster Allocation Matrix v1 (Section 7) |
| Create/confirm Cluster Leads chat and add all confirmed leads (A18) | Cizarina | 7 Aug | Live chat |
| Identify KICD/KUCCPS contact persons and send first outreach (A19) | Dr Muthoni + WG8 liaison | 7 Aug (initiate) | Contact log started |
| Submit WG2's mentorship-time requirement to Secretariat/WG4 (A20 input) | Dr Muthoni | 7 Aug | Written requirement (e.g. "minimum 90 min mentorship per cohort") |
| Give WG8 the cluster count, room needs, and timing for the student-guide route (A31 input) | Dr Muthoni + Cizarina | 7 Aug | Shared with WG8 |
| Send preferred emails to Iteyo Khaisia (A14) | All WG2 members | 7 Aug | Drive access |
| Prepare a 2-minute WG2 status update for SteerCo Meeting 2 | Cizarina or Dr Muthoni | 7 Aug, 1900hrs | Attend the meeting (R12) |

### Phase 1 — Week 1: Foundation (Sat 8 – Fri 14 Aug)

| Task | Owner | Target | Output |
| --- | --- | --- | --- |
| Confirm Cluster Lead + Sub-Lead for all 23 clusters, especially the new/recommended ones (Mining & Extractives, Agriculture & Agribusiness, Supply Chain, Uniformed & National Security Services — see Section 7.2) | Zone Coordinators | 11 Aug | Full leadership coverage |
| Open mentor recruitment drive (alumnae network, professional contacts, past mentors) | All WG2 | Ongoing | Mentor pipeline, target 85–100 mentors (Section 8.4) |
| Stand up the Mentor Database (Section 9) and start logging every contact | Interns | 9 Aug, then ongoing | Live tracker |
| Get Grade 10 / Form 4 headcounts and room capacities from WG8; confirm AM/PM shift timings (Section 8.5) | Cizarina | 10 Aug | Student grouping inputs |
| Set mentor-to-student ratio and cluster size formula (Section 10) | Dr Muthoni | 11 Aug | Grouping methodology |
| Draft Mentorship Strategy Document (objectives, learner outcomes) | Dr Muthoni + Cizarina | 12 Aug | v1 for SteerCo review |
| Draft Cluster Discussion Guide (topics/prompts per cluster, per cohort) | WG2 members (2–3 volunteers) | 13 Aug | v1 draft |
| Draft Mentor Handbook v1 (roles, schedule, safeguarding, FAQs) | Cizarina + interns | 14 Aug | v1 draft |
| Continue KICD/KUCCPS engagement; confirm expert headcount and decide rotating-corner vs. joint-session model (Section 7.5) | Dr Muthoni | 14 Aug | Confirmed experts + labs |
| Share mentor-numbers-needed with WG3 Comms for the mentor call (A25) | Cizarina | 8 Aug | WG3 briefed |

### Phase 2 — Week 2: Build & Brief (Sat 15 – Fri 21 Aug)

| Task | Owner | Target | Output |
| --- | --- | --- | --- |
| Finalise the Cluster Allocation Matrix (mentors, rooms, time slots, cohorts) | Dr Muthoni + Cizarina + Zone Coordinators | 17 Aug | Matrix v2 (near-final) |
| Finalise student-to-cluster assignment with WG8 | Cizarina + WG8 liaison | 18 Aug | Assignment list |
| Finalise Mentor Handbook and Cluster Leader SOP (Section 12) | Cizarina | 18 Aug | Final versions |
| Schedule and hold the Mentor Briefing Session; prepare briefing slides | Dr Muthoni | Session by 20 Aug | Mentors oriented |
| Coordinate with WG7 Booths on which booths complement each cluster topic | Cizarina | 19 Aug | Cluster–booth map |
| Confirm teacher/Chaplain integration into clusters (A32) | Dr Muthoni + WG8 | 20 Aug | Support roles assigned |
| Feed mentor confirmation numbers to WG3 for appreciation/reminder content | Cizarina | Ongoing | WG3 supplied |

### Phase 3 — Week 3: Confirm & Rehearse (Sat 22 – Fri 28 Aug)

| Task | Owner | Target | Output |
| --- | --- | --- | --- |
| Send final logistics to every confirmed mentor (venue, time, room, parking, dress code, AM/PM shift) | Interns | 24 Aug | Mentors informed |
| Attend the SteerCo recce of KHS rooms (A35); confirm each cluster's room fits both shifts | Dr Muthoni + Cizarina | When scheduled | Room sign-off |
| Finalise the Escalation Plan (no-shows, overcrowding, room changes — Section 14) | Cizarina | 25 Aug | Plan circulated to Zone Coordinators |
| Prepare on-the-day materials: signage, attendance sheets, discussion guides, feedback QR codes | Interns | 27 Aug | Printed/ready |
| Rehearse student movement (opening → mentorship → labs → booths → plenary → closing) with WG8 | Cizarina | 26 Aug | Route confirmed |
| Final check-in call with all Cluster Leads and Zone Coordinators | Dr Muthoni | 27 Aug | Everyone briefed and confirmed |
| Reconfirm KICD/KUCCPS attendance and lab logistics | Dr Muthoni | 27 Aug | Written confirmation |

### Event Day — Saturday 29 August

| Task | Owner |
| --- | --- |
| Zone Coordinator present and active, moving across their zone's clusters throughout both shifts | 5 Zone Coordinators |
| Roving oversight — Cizarina covers Zones B+C+E, Margaret covers Zones A+D (Section 8.2) | Lead + both Asst Leads |
| Live escalation contact reachable by phone/WhatsApp throughout | Cizarina + Margaret |
| Distribute mentor feedback form/QR at the close of each mentorship session | Cluster Leads |
| Track attendance (mentors and students) per cluster | Cluster Sub-Leads |

### Post-Event (from Sun 30 Aug)

| Task | Owner | Target |
| --- | --- | --- |
| Compile mentor feedback results | Interns | 2 Sep |
| Send mentor thank-you/appreciation messages (with WG3) | Cizarina | 2 Sep |
| Draft Post-Event Impact Report (participation, engagement, lessons, recommendations — Section 16) | Dr Muthoni + Cizarina | 5 Sep |
| Update Mentor Database and Cluster Reference for future Career Days | Interns | 5 Sep |

## 6. RACI — Who Owns What

R = Responsible (does the work) · A = Accountable (signs off) · C = Consulted · I = Informed

| Deliverable | Dr Muthoni (Lead) | Cizarina & Margaret (Asst Leads) | Zone Coordinators | Cluster Leads/Members | Interns | Secretariat | WG8 School |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cluster Structure & Zone Assignment (Section 7–8) | A | R | R | C | I | I | C |
| Cluster Allocation Matrix | A | R | R | R | C | I | C |
| Mentor Database | I | A | C | C | R | I | I |
| Mentorship Strategy Document | A | R | C | C | I | C | I |
| Mentor Handbook | A | R | C | C | R | I | I |
| Cluster Leader SOP | A | R | R | C | I | I | C |
| Mentor Briefing Session | R | A | R | C | R | I | I |
| Mentor Feedback Tool (A21) | A | R | I | I | R | I | I |
| KICD/KUCCPS Coordination (A19) | R | C | C | I | I | I | R/C |
| Protect Mentorship Time (A20) | R | C | I | I | I | A | C |
| Student-Guide Route Input (A31) | C | R | C | I | I | I | A |
| Teacher/Chaplain Integration (A32) | C | R | C | I | I | C | A |
| Post-Event Impact Report | A | R | C | C | R | I | I |
| Room & AV Setup (event day, target 9:00am ready) | I | I | C | R/A (Sub-Lead) | I | R | I |

Room & AV Setup was a real gap — nothing in the original Action Log or Task Tracker assigned it. It's now owned as described: Cluster Sub-Leads confirm their own room and AV before each cohort's window, Interns run the pre-doors sweep and stay on call for AV issues all day, and there is no separate "AV/Tech Support" role — it's folded into the existing Intern duties. Full detail in the companion Event-Day Setup, AV & Roles SOP (Section 20).

## 7. Cluster Structure — Reorganized for Best-Fit, Exhaustive Coverage (2026)

### 7.1 Why This Was Reorganized

The 2023 list of 18 clusters was a real asset — comprehensive and field-tested — but it had structural overlaps and gaps: Manufacturing sat under Entrepreneurship (it's really an engineering/operations career); Energy appeared in two unrelated clusters; agriculture was split between "Eco-Agriculture" (Environment) and "Agri-Business" (Entrepreneurship) with no home for core agronomy/animal husbandry/fisheries; Mining had no home at all; and "STEM" crammed 17 unrelated fields — from AI to biomedical engineering — into a single room, too broad for a focused mentorship conversation.

The reorganization below fixes each of those: every sub-field now has exactly one clear home, and the gaps identified in this conversation (Mining, standalone Agriculture, Supply Chain, Uniformed & Security Services) are folded in. The trade-off is size: the list grows from 19 to 23 clusters. That's a heavier operational lift — more rooms, more mentors — so Section 7.2 tiers every cluster by how essential and how easy-to-staff it is, with a mergeable fallback for each new one, in case Week 2 mentor recruitment runs short.

### 7.2 The 23 Clusters, Grouped into 5 Zones

| ID | Cluster | Tier | What Changed |
| --- | --- | --- | --- |
| A1 | Medical Practitioners | Core | Unchanged |
| A2 | Public Health & Psychosocial Services | Core | Unchanged |
| A3 | Sports Science & Physical Fitness | Core | Unchanged |
| B1 | Computing, Data & Cyber Sciences | Core | Split out of the old STEM cluster — recruit specifically for AI/ML, Data Science, Cyber Security |
| B2 | Engineering & Manufacturing | Core | Manufacturing moved here from Entrepreneurship — it's an engineering/operations career, not a startup one |
| B3 | Earth Sciences, Energy & Mining | New/Recommended | Resolves Energy appearing twice in the old list; Mining had no home at all — narrow mentor pool, source early |
| B4 | Environment & Conservation | Core | Eco-Agriculture moved out to B5; Energy moved out to B3 |
| B5 | Agriculture, Food & Agribusiness | New/Recommended | New standalone — consolidates Eco-Agriculture and Agri-Business plus core agriculture fields that had no home |
| B6 | Aviation, Aerospace & Maritime | Niche | Unchanged, plus optional Maritime sub-field |
| C1 | Finance & Actuarial Sciences | Core | Unchanged |
| C2 | Entrepreneurship & Innovation | Core | Now purely venture-building — Manufacturing/Agri-business moved out |
| C3 | Leadership & Strategic/HR Management | Core | Supply Chain moved out to C4 |
| C4 | Supply Chain, Logistics & Procurement | New/Recommended | Split out of Leadership — distinct field, was previously invisible |
| C5 | Marketing, PR, Sales, Comms & CX | Core | Unchanged |
| D1 | Legal Practitioners | Core | Unchanged |
| D2 | International Relations, Development & Governance | Core | Unchanged |
| D3 | Uniformed & National Security Services | New/Recommended | Proposed addition — interest level is my inference, not confirmed data; validate with WG8/students |
| D4 | Theology & Pastoral Care | Core | Unchanged |
| D5 | Education | Core | Unchanged |
| E1 | Journalism & The Media | Core | Unchanged |
| E2 | Hospitality & Tourism | Core | Flag TVET-track sub-fields (culinary/events trades) |
| E3 | The Arts (Applied/Visual/Performing/Literary) | Core | Flag TVET-track sub-fields (cosmetology/sound eng/design trades) |
| E4 | The Built Environment & Real Estate | Core | Unchanged — Energy Assessors retained here deliberately (building energy efficiency, a different job from B3's power-sector Energy) |

Full sub-field lists, tiers, and mergeable fallbacks for every cluster are in WG2_Cluster_Reference_2026.csv (companion file — this is the master reference; treat the table above as a summary).

### 7.3 If Mentor Recruitment Runs Short — Fallback Merges

Each new/recommended cluster has a named fallback so you're never stuck without a plan:

| If short on mentors for... | Merge into... |
| --- | --- |
| B3 Earth Sciences, Energy & Mining | B4 Environment & Conservation |
| B5 Agriculture, Food & Agribusiness | Split back: Eco-Agriculture → B4, Agribusiness → C2 |
| C4 Supply Chain, Logistics & Procurement | C3 Leadership & Strategic/HR Management |
| D3 Uniformed & National Security Services | Drop entirely if no mentor contact can be sourced — don't run an empty room |

Zones B, C, and D are now larger (5–6 clusters each) than Zones A and E (3–4). Their Zone Coordinators (Hannah Gitonga, Tamara Ariba, Lorraine Muturi in the draft assignment — Section 8.6) may need a deputy; flag this when confirming coordinators in Phase 0.

### 7.4 Where KICD and KUCCPS Experts Sit

Per resolution R06, KICD/KUCCPS experts are not an additional cluster — they are embedded within cohort-specific labs. With likely only a handful of experts available, they cannot be in 23 rooms at once. Recommend one of two models, decided once expert headcount is confirmed (target: mid-Week 1):

- Rotating Pathways Corner: experts move zone to zone on a fixed schedule (15–20 minutes per zone per shift), covering 3–6 clusters each visit.

- Joint cohort session: if only 1–2 experts are available, run one dedicated 25–30 minute KUCCPS/pathways explainer per cohort, with all zones breaking simultaneously, rather than trying to distribute experts thinly across every cluster.

### 7.5 CBC Pathway Alignment (Grade 10 Reference)

Kenya's CBC Senior School organises learners into three broad pathways — STEM, Social Sciences, and Arts & Sports Science — plus a cross-cutting TVET track. Mapping the clusters loosely helps Grade 10 students connect mentorship to the pathway choice they're making. Confirm final wording with the KICD expert before finalising signage, since pathway definitions are still being refined nationally.

| CBC Pathway | Aligned clusters |
| --- | --- |
| STEM | B1, B2, B3, B4, B5, B6, A1, A2 |
| Social Sciences | D1, D2, D3, D4, D5, C1, C2, C3, C4, C5, E1, E2 |
| Arts & Sports Science | A3, E3 |
| TVET (cross-cutting) | Sub-fields within E4, E2, E3, B5 (see Section 7.2) |

### 7.6 Cluster Allocation Matrix — What It Needs to Answer

This is the working artefact for A17. For each of the 23 clusters, capture: Zone, Cluster Lead, Sub-Lead, WG2 liaison/Zone Coordinator, mentors assigned, room, AM/PM time slot, cohort, target student count, and confirmation status.

A working template — pre-populated with all 23 clusters and their zones — is in WG2_Cluster_Allocation_Matrix.csv (companion file). The full sub-field reference list, tiers, and mergeable fallbacks are in WG2_Cluster_Reference_2026.csv.

## 8. Recommended Operational Structure — The Zone Model

### 8.1 Why a Zone Model

Twenty-three clusters is too many for WG2's leadership to personally oversee on the day — that's an unworkable span of control. Grouping the clusters into 5 Zones (Section 7.2), each with its own Zone Coordinator, turns "3 people overseeing 23 rooms" into "3 people overseeing 5 coordinators, each overseeing 3–6 rooms." That's manageable, and it matches what A17 is actually asking for: a WG2 liaison for every cluster, delivered through a coordinator layer rather than 23 separate direct reports.

### 8.2 Reporting Line — Now With Two Assistant Leads

Dr Muthoni has two confirmed Assistant Leads — Cizarina Nasirumbi and Margaret Ogachi. Rather than both overseeing all 5 Zones redundantly, split oversight so each owns a subset, grouped by domain fit rather than an even cluster count:

| Assistant Lead | Owns | Clusters |
| --- | --- | --- |
| Cizarina | Zone B (Engineering/Technology/Earth Sciences — STEM), Zone C (Business/Finance/Trade/Leadership), Zone E (Creative Industries/Media/Hospitality/Built Environment) | 15 |
| Margaret | Zone A (Health, Medicine & Human Performance), Zone D (Law/Governance/Public Service/Faith) | 8 |

This is a deliberately uneven split by cluster count (15 vs 8) — it groups zones by domain adjacency (STEM/Business/Creative under Cizarina; Health/Law-Governance-Faith under Margaret) rather than by headcount. Given the imbalance, Cizarina's zones should get first call on floater/deputy Zone Coordinator support (Section 8.6).

Mentor → Cluster Lead / Sub-Lead → Zone Coordinator (WG2 liaison) → Assistant Lead (Cizarina or Margaret, per zone above) → Lead (Dr Muthoni) → Secretariat

Every escalation, confirmation, and status update flows up this line. Zone Coordinators are the single point of contact WG2 needs to keep briefed — not every individual mentor. This split is a starting proposal — confirm the actual zone assignment with Cizarina and Margaret based on interest/network, same as the Zone Coordinator draft below.

### 8.3 The 5 Zones

| Zone | Clusters (count) | Assistant Lead Oversight | Suggested Zone Coordinator profile |
| --- | --- | --- | --- |
| A — Health, Medicine & Human Performance | 3 | Margaret | Member with health/medical network |
| B — Engineering, Technology, Earth & Life Sciences (STEM) | 6 | Cizarina | Member with technical/engineering network — consider a deputy given size |
| C — Business, Finance, Trade & Leadership | 5 | Cizarina | Member with corporate/finance network — consider a deputy given size |
| D — Law, Governance, Public Service & Faith | 5 | Margaret | Member with legal/public-service/faith network — consider a deputy given size |
| E — Creative Industries, Media, Hospitality & Built Environment | 4 | Cizarina | Member with creative/media/hospitality network |

### 8.4 Staffing Minimums per Cluster

- 1 Cluster Lead + 1 Sub-Lead minimum per cluster (mandatory — this is exactly what A17 requires WG2 to check).

- 2–6 mentors per cluster depending on expected demand and room capacity — niche clusters (Aviation/Aerospace/Maritime, Theology & Pastoral Care, Uniformed & National Security Services) can run on 2; high-demand clusters (Computing/Data/Cyber, Medical Practitioners, Finance) should target 4–6. Exact recommended minimums per cluster are in WG2_Cluster_Reference_2026.csv.

- Summed across all 23 clusters, the baseline is ~68 mentors. Target at least 65–70 confirmed mentors as a floor, and recruit toward 85–100 to build in a ~20–25% no-show buffer given the larger cluster count.

### 8.5 Shift Model (Now Locked — Three Cohorts, Sequential, Not Two Passes)

Updated 17 Aug — supersedes the two-pass draft below. The locked schedule (Section 18, the WG2 App's Revision 3) runs three cohorts — Form 4, Grade 10 Group A, Grade 10 Group B — through the same 23 rooms sequentially, one after another, not as a single AM pass and a single PM pass. Each room hosts Form 4's mentorship window first (10:45am–12:15pm), then Grade 10 Group A's (1:00–2:30pm), then Grade 10 Group B's (2:30–4:00pm).

This still delivers the two benefits the original two-pass model was designed for, just via three sequential windows instead of two:

- Room count needed = 23, not 69 — confirmed. The Cluster Allocation Matrix and the WG2 App both run on 23 rooms; this is no longer an open dependency (contrast Section 18.7).

- Mentors can commit to a single shift. The WG2 App's Team records carry a shifts field with exactly two practical options: Morning (covers only Form 4's window, 10:45am–12:15pm) and Afternoon (covers both Grade 10 waves back-to-back, 1:00–4:00pm) — plus Either/Both for mentors free the whole day. A mentor who can only do a Saturday morning is still eligible; they're just never scheduled for the Grade 10 windows.

Content should still differ by cohort even where the cluster theme doesn't: Grade 10 sessions should stay exploratory (what does this field actually involve, what subjects/pathway feed into it); Form 4 sessions should get concrete (KUCCPS course selection, cut-off points, degree vs. TVET vs. gap-year decisions).

### 8.6 Zone Coordinator Assignment — Confirm in Phase 0

Draft suggestion from the current confirmed WG2 Members (Zone Coordinators should come from Members, not Interns, given the reporting responsibility) — confirm actual fit against interest/network during Phase 0:

| Zone | Draft candidate | Reports to | Clusters | Confirm by |
| --- | --- | --- | --- | --- |
| A — Health, Medicine & Human Performance | Anne Obure | Margaret | 3 | 6 Aug |
| B — Engineering, Technology, Earth & Life Sciences (STEM) | Hannah Gitonga (+ deputy recommended) | Cizarina | 6 | 6 Aug |
| C — Business, Finance, Trade & Leadership | Tamara Ariba (+ deputy recommended) | Cizarina | 5 | 6 Aug |
| D — Law, Governance, Public Service & Faith | Lorraine Muturi (+ deputy recommended) | Margaret | 5 | 6 Aug |
| E — Creative Industries, Media, Hospitality & Built Environment | Mercy Amuguni | Cizarina | 4 | 6 Aug |

Sharon Chachale-Wata and Wangechi Ndirangu (also WG4 Plenary Lead) can act as floaters/deputies for Zones B, C and E, which now all sit under Cizarina and together carry 15 of the 23 clusters. Adjust freely — this is a starting proposal, not a fixed assignment.

## 9. Mentor Database — What It Tracks

Every mentor needs a row from first contact to post-event: name, contact details, profession/expertise, which cluster and cohort they're assigned to, role (Cluster Lead / Sub-Lead / Mentor), confirmation status, whether they attended the briefing, and any notes (replacement needed, dietary/access needs, etc.).

Also tracks a secondary cluster. Every mentor application asks whether they're willing to help fill a gap in a second cluster beyond their first choice. That answer now survives all the way from application into the Mentor Database (secondaryClusterIds/secondaryClusterNames) — a data-loss bug that silently dropped it on approval was found and fixed 17 Aug. This is what powers the WG2 App's gap-filling suggestions (Section 20): for any cluster short on mentors, the app can now surface real people who already said they'd help there, not just a cold-recruitment list.

A working template, seeded with the confirmed WG2 team as a starting point, is in WG2_Mentor_Database.csv (companion file) — though the live version now lives in the WG2 App's own Google Sheet, which is the one the app's Reports and gap-suggestion features actually read from.

## 10. Student Grouping Methodology

Define before assigning students to clusters:

- Confirmed numbers (per WG8): 1,246 total learners — Form 4: 450, Grade 10: 796 (special arrangement).

- Cohort split: Grade 10 and Form 4 move through mentorship separately (staggered model, R04) — content and depth should differ (exploration vs. transition-to-university/career). See Section 18 for the full event-day schedule this drives.

- Mentor : student ratio: recommend no more than 1 mentor per 10–15 students per discussion group for genuine interaction; large clusters should split into sub-groups under the same Cluster Lead.

- Cluster size, as calculated: Form 4 (450 ÷ 23 clusters) ≈ 20 students/cluster in a single pass. Grade 10 (796 ÷ 23 clusters) ≈ 35 students/cluster in a single pass — too many for genuine mentorship, which is why Section 18 recommends splitting Grade 10 into two mini-waves of ~398 (≈17 students/cluster/wave) through the same 23 rooms rather than requesting extra rooms.

- Assignment logic: either (a) students pre-select a cluster by interest (requires a sign-up form before the day — consider aligning the sign-up categories to the CBC pathway mapping in Section 7.5 so Grade 10 learners can self-select meaningfully), or (b) students are pre-assigned by class/stream to balance clusters evenly. Recommend confirming this with WG8 in Week 1, since it drives the student-guide route (A31).

## 11. Mentor Feedback Tool — Draft Questions

Delivered. This no longer needs a separate Google Form build — the WG2 App has a built-in Mentor Feedback Survey, filled in-app on or immediately after Career Day. Keep it to under 10 questions, mobile-friendly, completed before mentors leave the venue.

Which cluster/cohort did you mentor today?

How would you rate the organisation of your session? (1–5)

Were the students well-prepared and engaged? (1–5)

Did you have everything you needed (room, materials, time)? (Yes/No + comment)

What worked well?

What should be improved next time?

Would you be willing to mentor again at a future Career Day? (Yes/No/Maybe)

Any other comments?

## 12. Cluster Leader SOP (Draft Outline)

Before the day: confirm attendance, review the discussion guide, know your room and time slot, know your Zone Coordinator's contact.

On arrival: check in with your Zone Coordinator, confirm mentor headcount, confirm room setup.

Facilitation: keep to time, ensure every student gets to speak/ask a question, steer toward practical guidance (not just career war-stories).

Timekeeping: hard stop at the scheduled end time to protect the next rotation/cohort.

Escalation: if a mentor doesn't show, or the room is overcrowded, contact your Zone Coordinator immediately — do not try to solve it silently (see Section 14).

Close-out: distribute the mentor feedback form/QR before mentors leave; report headcount to your Zone Coordinator.

Superseded by a fuller document. This outline still holds, but it only ever covered Cluster Leads. The companion WG2 Role SOPs — Everyone's What, When, Where (Section 20) now gives every WG2 role — Lead, Assistant Leads, Zone Coordinators, Cluster Leads, Sub-Leads, Mentors, Interns, and the Class Teacher/WG8 Liaison — the same before/during/escalation/impact treatment, grounded in the actual locked schedule (Section 18). Use that document as the day-of quick reference; keep this outline as the original source for Cluster Leads specifically.

## 13. Mentor Briefing Session — Agenda Outline

Target: hold in Week 2, 45–60 minutes, virtual or in-person.

Welcome + why mentorship matters this year (mentorship > plenary — R05)

Career Day overview: theme, cohorts, shifts, schedule, venue map, zone structure

Your cluster: room, time, co-mentors, discussion guide walkthrough

Facilitation tips + safeguarding guidance (working with minors)

Logistics: arrival time, sign-in, dress code, parking, contacts

Q&A

Feedback form preview

## 14. Escalation & Risk Log

| Risk | Response | Owner |
| --- | --- | --- |
| Mentor no-show | Sub-Lead absorbs group; Zone Coordinator texts backup mentor list | Zone Coordinator |
| Cluster overcrowded | Zone Coordinator redirects overflow to nearest same-theme cluster or holding area | Zone Coordinator |
| Room change needed | Zone Coordinator confirms new room with WG8 on-site contact, updates signage | Zone Coordinator + WG8 |
| KICD/KUCCPS expert delayed/absent | Cluster Lead runs a Q&A/discussion holding activity until they arrive | Cluster Lead |
| Whole zone in trouble (multiple issues at once) | Zone Coordinator escalates directly to Cizarina/Dr Muthoni | Cizarina/Dr Muthoni |
| Student late arrival between rotations | Directed by WG8 routing volunteers per the student-guide route | WG8 |
| Screen/device fails mid-session (AV) | Sub-Lead switches to a verbal/discussion-only format for the rest of that window; flags the Intern AV team before the next window | Cluster Sub-Lead |
| Wi-Fi drops during a Live virtual session | Try the mentor's own hotspot/data; otherwise the mentor calls in by phone, or the session pauses and it's noted in the close-out report | Cluster Sub-Lead |
| Multiple rooms report AV issues at once | Intern AV team triages by cluster demand tier; escalates to Zone Coordinator if unresolved before the next window | Interns + Zone Coordinator |

Fuller escalation ladder available. The rows above are the risk-specific responses; for the full reporting chain (who calls whom, and who they call next if it's still unresolved), see the companion WG2 Role SOPs document's Escalation Ladder (Section 20) and the Event-Day Setup, AV & Roles SOP for AV-specific detail.

## 15. Coordination Map

| Relationship | What WG2 needs from them | What WG2 gives them |
| --- | --- | --- |
| Secretariat | Programme timing decisions, escalation support, Drive/comms access | Roster, workplan, status updates for SteerCo meetings |
| WG8 School (most critical) | Room capacity for 23 rooms across 2 shifts, cohort headcounts, teacher/Chaplain contacts, student routing plan | Cluster count (23) and zone map, room/timing needs, cluster locations for signage |
| WG4 Plenary | Visibility into programme draft to negotiate mentorship time | Minimum mentorship time requirement, KICD/KUCCPS placement needs — note: this is the full extent of the relationship. WG2 has no planning, staffing, or AV role in the Opening or Closing Plenary itself; it's entirely WG4's (confirmed 17 Aug, see Section 18 and the Event-Day Setup SOP's Out of Scope section) |
| WG3 Comms | Mentor call message distribution, appreciation content | Mentor numbers, confirmations, updates, reminders needed |
| WG7 Booths | Booth themes/exhibitor list | Cluster topics, so students can move naturally from mentorship to related booths |

## 16. Success Metrics & Post-Event Impact Report

Track beyond attendance:

- Mentor confirmation rate (confirmed ÷ invited), and by cluster/zone

- Mentor show-up rate on the day

- Mentor feedback scores (organisation, student engagement)

- Student:mentor ratio achieved per cluster vs. target

- Mentor willingness-to-return rate

- Which clusters were over/under-subscribed (informs the 2027 cluster list)

- Qualitative highlights and gaps (from feedback free-text)

Post-Event Impact Report (target: 5 Sep) should summarise all of the above plus lessons learned and recommendations for the next Career Day — including whether the new Uniformed & National Security Services cluster and the Zone model should carry forward.

## 17. Full WG2 Checklist (Foundation Through Post-Event)

Rewritten 17 Aug 2026. This used to cover only "this week" (5–7 Aug), which is now long past and mostly done. Below is the complete checklist across every phase, so it stays useful as a full reference rather than a single stale week. Checkbox state here is not the live record — the WG2 App's Google Sheet is. Treat every box below as "does this still need doing," not as an up-to-date tracker; a lot of the earlier items are already done.

Foundation (roster, structure, zones)

- ☐ Confirm WG2 Lead and both Assistant Leads

- ☐ Confirm the 23-cluster / 5-zone structure (Section 7)

- ☐ Appoint 5 Zone Coordinators (Section 8.6) — reconfirm against the current roster (Section 20 flags a possible change)

- ☐ Draft and upload the WG2 roster & structure doc

- ☐ Submit the WG2 budget to WG1 Finance — new requirement, not previously tracked here (Section 4, A02)

- ☐ Assign a Zone Coordinator/liaison to every cluster; check Cluster Lead/Sub-Lead availability

- ☐ Create/populate the Cluster Leads WhatsApp chat

- ☐ Everyone sends their preferred email for Drive/calendar access

Mentor recruitment & materials

- ☐ Open the mentor recruitment drive across all 23 clusters, prioritising B3/B5/C4/D3 (Section 7.2)

- ☐ Stand up and maintain the Mentor Database — now the WG2 App's own Sheet (Section 9)

- ☐ Get Grade 10 / Form 4 headcounts and room capacities from WG8; confirm shift timings

- ☐ Set the mentor-to-student ratio and cluster size formula (Section 10)

- ☐ Draft the Mentorship Strategy Document

- ☐ Draft the Cluster Discussion Guide (topics/prompts per cluster, per cohort)

- ☐ Draft the Mentor Handbook (roles, schedule, safeguarding, FAQs)

- ☐ Engage the KICD and KUCCPS experts; confirm headcount and rotating-corner vs. joint-session model (Section 7.4)

- ☐ Validate learner interest in the Uniformed & National Security Services cluster (Section 4, A09)

Build & brief

- ☐ Finalise the Cluster Allocation Matrix (mentors, rooms, time slots, cohorts)

- ☐ Finalise student-to-cluster assignment with WG8

- ☐ Finalise the Mentor Handbook and Cluster Leader SOP (Section 12; see also the full Role SOPs, Section 20)

- ☐ Schedule and hold the Mentor Briefing Session

- ☐ Confirm the Mentor Feedback Tool is live in the app (Section 11)

- ☐ Coordinate with WG7 Booths on cluster–booth alignment

- ☐ Confirm teacher/Chaplain integration into the relevant cluster chats (Section 4, A09 in the new Action Log)

Confirm & rehearse

- ☐ Send final logistics to every confirmed mentor (venue, time, room, shift)

- ☐ Attend the SteerCo recce of KHS rooms; confirm every cluster's room fits all three cohort windows

- ☐ Finalise the Escalation Plan (Section 14) and circulate to Zone Coordinators

- ☐ Prepare on-the-day materials: signage, attendance rosters, discussion guides, feedback QR codes

- ☐ Rehearse student movement with WG8 (Section 18.6)

- ☐ Final check-in call with all Cluster Leads and Zone Coordinators

- ☐ Reconfirm KICD/KUCCPS attendance and lab logistics

Event-day setup (see the Event-Day Setup, AV & Roles SOP, Section 20, for full detail)

- ☐ All 23 rooms and AV ready by 9:00am

- ☐ Pre-doors AV sweep completed

- ☐ Zone Coordinators, Cluster Leads, Sub-Leads and Mentors checked in per their shift

Post-event

- ☐ Compile mentor feedback results

- ☐ Send mentor thank-you/appreciation messages (with WG3)

- ☐ Draft the Post-Event Impact Report (Section 16)

- ☐ Update the Mentor Database and Cluster Reference for future Career Days

## 18. Event Day Master Schedule (Saturday 29 August 2026)

Confirmed numbers from WG8: 1,246 total learners — Form 4: 450, Grade 10: 796 (special arrangement, split into Group A: 398 and Group B: 398). Classroom capacity confirmed at ~45 students. Food is provided by the school as usual — catering is not a WG2 dependency.

Rewritten 17 Aug 2026. This section previously described an earlier planning draft (a 3-slot model starting at 07:00 with WG2 running a combined Opening/Closing Plenary). That draft has been superseded by the locked schedule the WG2 App now actually runs on — Revision 3, dated 15 Aug 2026. Two things changed: the day starts later (mentorship begins 10:45am, after the school's own cocoa break, not 07:00am), and WG2 has zero role in the Opening or Closing Plenary — it's entirely WG4's, and isn't modelled anywhere below. If either fact is wrong by the time you're reading this, the live source of truth is the Schedule sheet the app writes to, not this document — flag any mismatch to Cizarina so both get corrected together.

### 18.1 The Three-Cohort Sequential Model

The 23 cluster rooms host all three cohorts in sequence, one after another — Form 4's mentorship window first, then Grade 10 Group A's, then Grade 10 Group B's — never two cohorts mentoring in the same room at once. While a given cohort is in its own mentorship window, the other two are in Lab sessions or an Exhibition/Lunch block, run in separate space so they don't compete for the 23 rooms.

- Form 4 (450): mentorship 10:45am–12:15pm, all 23 cluster rooms

- Grade 10 Group A (398): mentorship 1:00pm–2:30pm, same 23 rooms, reused

- Grade 10 Group B (398): mentorship 2:30pm–4:00pm, same 23 rooms, reused

Grade 10 A/B at 398 each ÷ 23 clusters ≈ 17 students/cluster/round — comfortably under the 45-seat cap and better for genuine mentorship than a single 796-strong pass (≈35/cluster) would be. Every cohort finishes its last scheduled block by 4:00pm sharp.

### 18.2 Mentorship Round Structure

Each cohort gets exactly 3 standard rounds of 25 minutes with a 5-minute changeover (a 30-minute unit, 90 minutes total for the 3 rounds), plus an optional 4th round for students who arranged it in advance with WG2 — this is an either/or alternative to that cohort's second Exhibition window sharing the same time slot, not an addition on top of it, and which Exhibition it swaps out differs by cohort (see the table below and the WG2 App for each cohort's swap).

### 18.3 Full Day Schedule, Per Cohort

Setup target: rooms and AV fully ready by 9:00am, before any cohort's first block (see the companion Event-Day Setup, AV & Roles SOP, Section 20). Blocks marked "Not WG2" are shown for context — WG2's cluster-room roles (Cluster Lead, Sub-Lead, Mentors) are not staffed there; Lab sessions run with KICD/KUCCPS experts, coordinated with WG8 (Section 7.4).

Form 4 (450 students)

| Time | Block | WG2 role |
| --- | --- | --- |
| 10:45–11:15 | Mentorship Round 1 | Active |
| 11:15–11:45 | Mentorship Round 2 | Active |
| 11:45–12:15 | Mentorship Round 3 | Active |
| 12:15–12:40 | Round 4 (pre-arranged extra) OR Exhibition 1 | Active only if a Round 4 was pre-arranged |
| 12:40–13:00 | Lunch | Not WG2 |
| 13:00–14:00 | Lab 1 | Not WG2 |
| 14:00–15:00 | Exhibition 2 (compulsory) | Not WG2 |
| 15:00–16:00 | Lab 2 | Not WG2 |

Grade 10 — Group A (398 students)

| Time | Block | WG2 role |
| --- | --- | --- |
| 10:45–11:45 | Lab 1 | Not WG2 |
| 11:45–12:15 | Exhibition 1 (compulsory) | Not WG2 |
| 12:15–13:00 | Lunch | Not WG2 |
| 13:00–13:30 | Mentorship Round 1 | Active |
| 13:30–14:00 | Mentorship Round 2 | Active |
| 14:00–14:30 | Mentorship Round 3 | Active |
| 14:30–15:00 | Round 4 (pre-arranged extra) OR Exhibition 2 | Active only if a Round 4 was pre-arranged |
| 15:00–16:00 | Lab 2 | Not WG2 |

Grade 10 — Group B (398 students)

| Time | Block | WG2 role |
| --- | --- | --- |
| 10:45–11:45 | Lab 1 | Not WG2 |
| 11:45–12:15 | Exhibition 1 (compulsory) | Not WG2 |
| 12:15–13:00 | Lunch | Not WG2 |
| 13:00–14:00 | Lab 2 | Not WG2 |
| 14:00–14:30 | Round 4 (pre-arranged extra) OR Exhibition 2 | Active only if a Round 4 was pre-arranged |
| 14:30–15:00 | Mentorship Round 1 | Active |
| 15:00–15:30 | Mentorship Round 2 | Active |
| 15:30–16:00 | Mentorship Round 3 | Active |

Full per-role timelines (what each role does at each of these blocks) are in the companion WG2 Role SOPs document (Section 20) — this table is the shared schedule of record both documents are built from.

### 18.4 Pre-Registration System

Hard deadline: fully ready by Thursday 27 August — 2 days before Career Day. Everything below (collection, allocation, itinerary cards, wristbands) works backward from that date so WG8/teachers have a full clear day (28 Aug) to rehearse room readiness with no open registration questions left. This is required to run the round system at all — students can't be found rooms in real time on a 30-minute cycle.

Updated for the WG2 App (see WG2_Team_App_Setup_Guide.docx and khs-team-app/): the stages below used to run as five separate tools — a Google Form, a manual allocation pass, a raw Sheet link, a QR API, and a mail-merge template. They now run through one app, backed by the same free Google Sheet, so there's one place to check status instead of five.

Collect (opens 15 Aug once the Cluster Allocation Matrix is locked, closes 20 Aug): name, admission number, class/stream, cohort, and top 6 cluster interests in priority order, entered through the app's Register → Student form (grouped by Zone so the list of 23 isn't overwhelming; reference the CBC pathway mapping in Section 7.6 to help Grade 10 students connect choices to their pathway). Six choices gives the allocation pass room to work when popular clusters (Computing/Data/Cyber, Medical) are oversubscribed — a student's top 4 still-available choices become their Round 1–4 itinerary. Run this as an in-class session led by WG8 teachers (Section 19.5): either a teacher/intern types each student's choices into the app directly, or — for a faster in-class pass — collects them on paper first and pastes the whole class in at once via Register → Bulk Import (CSV). Either way, a QR code is generated instantly the moment a student is registered — no separate QR-generation step, and no waiting for the Form to close before anyone sees their code.

Allocate (Zone Coordinators or a WG2 intern, 21–23 Aug, but can be re-run any time after — it only fills in what's missing): open the app's Dashboard and tap Run Allocation. This runs the same logic that used to be done by hand — cap each cluster's seats per round, assign each student her highest-ranked still-available cluster, cascading down her list if a choice is full, with no student repeating a cluster across her 4 rounds — but now it runs in seconds instead of a multi-day manual pass, and Form 4/Grade 10 A/Grade 10 B are allocated independently so the three cohorts never compete for the same seats. Each student's Registration ID (Section 19.1) is assigned automatically the moment she's registered, not as a separate step.

Confirm digitally (24–26 Aug): teachers open the app's Schedule → My Class view, filtered automatically to their own stream — no separate link to distribute or permissions to manage — and project or share it in class. This is the "confirmation" step: every student sees her actual Rounds and Rooms digitally before anything is printed.

Produce and publish (24–26 Aug): every student's QR already exists from the moment she registered (Register → Download QR). If a physical Itinerary Card (Round 1–4: cluster + room + Registration ID/QR, Section 19.2) is still wanted as a backup, it's a straightforward export from the same Students sheet the app writes to — the same mail-merge approach as before, just pointed at live app data instead of Form responses. Batch-exporting many QR codes at once for printing isn't built into the app yet (see the setup guide's "What's Next"); for now, download codes individually or via the sheet export.

Distribute (26–27 Aug, complete by 27 Aug): wristbands + printed QR Itinerary Cards (or, for students without a printed card, a live look-up via Schedule → Find Student on any shared phone/device) handed out in class with a short orientation on how the day will run, including how to use the Digital Day Guide (Section 19.7) if anyone loses their card or forgets a room. This is the line that must not slip — it's what "ready 2 days prior" means in practice: not just data collected, but physical materials (or a working app) in every student's hand with time to ask questions before the day.

Walk-in buffer: reserve ~10% headroom across clusters, or run a same-day sign-up desk for students who didn't pre-register, registering them on the spot via the app's Check-In → Walk-in tab (which registers and checks in, in one step) and routing them to under-subscribed clusters (Section 19.4).

### 18.5 Comparative Scenario: Mixed Batches Instead of Cohort-Segregated

An alternative is splitting all 1,246 into 3 mixed batches of ~415 each (blending Form 4 and Grade 10 proportionally, ~36%/64%) rather than keeping cohorts separate, using the identical sequential-cohort mechanics and the same overall day length — only who's in the room together changes.

Not recommended. R04 explicitly adopted a "two-cohort staggered" model, and R06 explicitly calls for "cohort-specific" mentorship labs. Mixing Form 4 (KUCCPS-application-ready) and Grade 10 (exploratory) in the same mentorship room at the same time forces mentors to serve both audiences in one conversation, diluting exactly the tailoring the resolutions ask for — and it removes cohort-specific labs too, since the same batch spans both cohorts. The only real case for mixing is if WG8 finds three symmetric batches easier to administer than the uneven 450/398/398 split, which is a minor convenience against a direct resolution conflict. Bring the cohort-segregated version (Section 18.1) as the recommendation, not both as equal options.

### 18.6 Execution Mechanics

Colour-code cohort wristbands (Grade 10 vs Form 4) at registration, and zone signage (5 colours matching Zones A–E) at every entrance. Station marshals at every junction on the student-guide route (A31) — corridor turns and the mentorship/lab swap points, not just zone entrances, since that's where 400–800 people moving at once will bottleneck. Use a PA announcement or bell for every transition. Spread water stations across all 5 zones. Set up one Command Post (Cizarina, Dr Muthoni, a WG8 lead, a Secretariat rep) reachable by a single WhatsApp broadcast group covering all Zone Coordinators. Put a WG3 photographer in each zone during mentorship windows. Run a 15-minute hot debrief at 16:00 while the day is fresh — this now lines up exactly with Grade 10 Group B's mentorship close, the last WG2-run block of the day.

This is WG2's execution plan for its own windows only — the Opening and Closing Plenary have their own staging and AV run entirely by WG4, not covered here.

### 18.7 Open Dependencies — Confirm Before Locking This Schedule

- Confirmed room count — resolved. All 23 clusters get a room in every cohort's mentorship window; this is what the Cluster Allocation Matrix and the WG2 App both run on. If WG8 can only offer fewer on the day, apply the fallback merges (Section 7.3) before the day, not on it.

- Lab venue capacity — nearly resolved. Each lab window must absorb up to 848 students (two cohorts combined) split by cohort into separate halls. WG8's own 7 August SteerCo Action Log now confirms the Old Dining Hall at 800–850 capacity for Labs (and the New Dining Hall at 1,300 for Plenary, WG4's concern, not WG2's) — close enough to the 848 need that this is nearly settled; get WG8's final written confirmation rather than treating it as still fully open.

- KICD/KUCCPS expert headcount — determines how many lab sessions can run cohort-specific content simultaneously, or whether some lab content has to be shared/recorded instead of live.

- Dining Hall/Plenary venue capacity (Action A34) — removed from this list, 17 Aug. A combined 1,246-person Plenary needing a venue that size is entirely WG4's planning concern; WG2 has no Plenary role (Section 2), so it's no longer tracked here.

## 19. Student Identification & Entry Tracking System

Answers the question raised on the 6 Aug call: with 1,246 students moving through 23 rooms across 4 rounds, how does anyone know who is supposed to be where, and catch it fast when someone isn't? Two layers, deliberately simple enough for teachers and Cluster Sub-Leads to run without training beyond a 10-minute walkthrough.

### 19.1 Layer 1 — Colour-Coded Wristbands (coarse, at-a-glance)

One wristband per student, issued at pre-registration distribution (27 Aug), worn all day. Purpose: a marshal at a glance can tell if a student is in the right general area, without checking a list. Updated 17 Aug 2026 — confirmed colours are Maroon, Yellow and Bright Pink (the earlier Green/Blue draft is no longer current):

| Colour | Group | Meaning |
| --- | --- | --- |
| Maroon | Form 4 | All 450 |
| Yellow | Grade 10 — Group A | ~398 |
| Bright Pink | Grade 10 — Group B | ~398 |

This alone lets marshals catch the most common error — a student in the wrong cohort's zone/slot — instantly and without a scanner. Cheap silicone festival-style wristbands or coloured paper bands both work; match by colour name when ordering rather than a specific hex/Pantone code, since none has been specified.

### 19.2 Layer 2 — Registration ID + QR Code (fine-grained, per-room)

Every pre-registered student gets a Registration ID in the format KHS26-[Cohort][Group]-[AdmissionNo] (e.g. KHS26-G10A-4021, KHS26-F4-1187). This ID is encoded as a QR code and printed on a personal Itinerary Card alongside her rounds. Below is a sample of how it actually looks (mocked-up data, not a real student):

The QR itself is generated the moment a student is registered in the WG2 App (Register tab), not as a separate batch step — the app builds the Registration ID from her cohort and admission number and renders the QR on-screen instantly, client-side, no external QR API or per-student manual step involved. If a printed physical card is still wanted (24–26 Aug, alongside allocation), it's a mail-merge from the same Students sheet the app writes to. No paid tool needed either way.

### 19.3 On-the-Day Scanning Process

At each room entrance, the Cluster Sub-Lead (not the mentor — keeps the mentor free to mentor) checks in incoming students using the WG2 App's Check-In → Scan QR tab on their own phone — tap Start Camera, point at each student's code, confirm the round and room, done. This logs Registration ID, timestamp, and room straight into the same Google Sheet the rest of the app reads from, so it also feeds the Dashboard's Live Today panel — Command Post (Section 18.6) can see in real time if a room is empty when it shouldn't be, or overcrowded, without needing a separate attendance Sheet to check. If the camera isn't available or a card is damaged, Check-In → Search looks a student up by name or ID instead — no scanning required.

If a scan doesn't match (student's QR says Room 14 but she's at Room 9): the Sub-Lead lets her in anyway — never turn a student away — and logs the actual round/room she's checking into via the confirm screen. This is a routing signal, not a discipline issue; most mismatches will be a friend group wanting to stay together, or a genuine wrong turn.

### 19.4 Low-Tech Fallback

Wi-Fi/data drops: the app itself keeps working — it caches the last-synced roster locally and queues check-ins on the phone, syncing automatically the next time it has a connection, so a brief drop mid-round doesn't require switching to paper at all. If a phone dies or is genuinely unusable, every Cluster Sub-Lead also has a printed paper roster for their room per round (same data as the Google Sheet, exported the morning of 29 Aug), and simply ticks names as students enter. The paper roster is the source of truth if the two ever disagree. Walk-ins without a pre-printed card are logged by hand on a blank line, or registered directly on a working phone via Check-In → Walk-in (Section 18.4), and issued a same-day Registration ID either way.

### 19.5 WG8 / Teacher Coordination

Ties into Action A32 (integrate teachers into Working Groups). The whole process — registration, confirmation, and day-of coordination — is run through digital tools that teachers operate directly, with paper only as the fallback (Section 19.4). Proposed division of labour:

| Stage | What teachers do | When |
| --- | --- | --- |
| Pre-registration collection | Run the WG2 App's Register → Student form (or Bulk Import (CSV) for a whole class at once) as an in-class session, on phones or a projected screen, so every student completes it under supervision — far more reliable than an unsupervised link | Week of 17 Aug, before the 20 Aug close |
| Digital confirmation | Once allocation runs, each teacher opens the WG2 App's Schedule → My Class view — automatically filtered to her own stream, no separate link or permissions to manage — showing every student's Rounds, Rooms, and Registration ID. Teacher projects or shares this in class so students see their confirmed placement digitally before cards are printed | 24–26 Aug |
| Distribution | Hand out wristbands + printed QR Itinerary Cards in class, with a short (10-min) orientation: what the wristband colours mean, how to scan/read the Digital Day Guide QR (Section 19.7), what to do if unsure | 26–27 Aug, complete by 27 Aug |
| Entrance staffing | Provide 1–2 teachers per zone (5 zones) as additional marshals alongside WG2 Zone Coordinators, focused on the corridor/junction points identified in Section 18.6 | Event day, per cohort window |
| Walk-in desk | Staff the same-day sign-up desk jointly with a WG2 intern, since teachers can verify a student's identity/class instantly — walk-ins are entered straight into the WG2 App's Check-In → Walk-in tab, which registers and checks in together | Event day, ongoing |
| Movement marshalling | Help move their own form/stream between mentorship and lab slots at transition points, pointing students to the Digital Day Guide (Section 19.7) if anyone loses track of where to go next | Event day, every transition |

Recommend Dr Muthoni raise this specific division of labour with the WG8 lead this week, so it can be confirmed alongside the room recce (A35) rather than as a separate conversation.

### 19.6 Remaining Tasks

Everything registration- and QR-related that used to be a separate build (Google Form, manual QR generation, entry-scanning form, attendance sheet) now runs through the WG2 App instead — no need to build any of that. What's actually left to do:

- Source and order wristbands (Maroon / Yellow / Bright Pink, ~1,250 units with buffer) — price and lead time need checking given the 27 Aug distribution deadline.

- Print Itinerary Cards (if wanted as a physical backup) and prepare the per-room paper roster fallback for 29 Aug — both are simple exports from the Students sheet the app already maintains.

- Deploy the WG2 App if this hasn't happened yet, and make sure every Zone Coordinator, Cluster Sub-Lead, and teacher liaison has the install link.

- Test the scanning process end-to-end with a small group before the day.

- Set up the Digital Class Roster views (one filtered view per class/stream) and share access with the right teacher.

- Build the Digital Day Guide page (Section 19.7) and generate its QR code for signage and the Itinerary Card.

- Build the printable Staff & Team Directory (Section 19.8) for the noticeboards.

Task assignment and status for all of the above lives in the WG2 App's own Tasks tab — the team doesn't need a separate spreadsheet reference for this; anyone who needs the full list can pull it straight from the app.

### 19.7 Digital Day Guide — Self-Service for Students & Teachers

A second, public QR code — separate from each student's private Registration ID QR — that answers "where do I go now?" without needing anyone to find a marshal. Solves the gap where a student loses her card, forgets her next room, or just wants to check the full day's flow.

What it is: one simple mobile-friendly page (a published Google Site or a Google Sheet published to the web works — no paid tool needed) containing:

- The full round-by-round clock for all three groups (Form 4, Grade 10 A, Grade 10 B), pulled straight from the Draft Programme.

- A simple zone/room map of the school for the day (which corridor, which zone colour, where the halls are).

- A live "any changes today" banner Command Post can edit in real time if a room moves or a slot runs late.

Where it appears: printed on every Itinerary Card, on a poster at every zone entrance, at the Command Post, and read out once at the opening plenary. Same link and QR for the whole school — nothing personalised, so it's simple to build and impossible for a student to "lose."

Why alongside the personal QR, not instead of it: the personal Registration ID QR (Section 19.2) is what Cluster Sub-Leads scan to log attendance — it's about tracking. The Digital Day Guide is what a student scans herself — it's about orientation. Different job, so both stay in the system; a student who's confident just follows her Itinerary Card, and this is the safety net for everyone else.

Not just for students. Most students won't be carrying phones on the day, but mentors, interns, Zone Coordinators and other team members will — and they're just as likely to need "where do I go now?" mid-shift, especially anyone covering an unfamiliar zone or stepping in as a last-minute replacement. The same QR/link works for them; no separate version needed.

### 19.8 Staff & Team Directory (Printable)

A one-page printable directory for mentors, interns and team members — who to find and where, for anyone unsure who's covering what during the day. Print this page and post it at the Command Post, each zone entrance, and the staff noticeboard. Fill in the phone column before printing; it's intentionally left blank here rather than guessed.

| Role | Name | Phone |
| --- | --- | --- |
| Lead | Dr Muthoni Mugambi |  |
| Assistant Lead (Zones B, C, E) | Cizarina Nasirumbi |  |
| Assistant Lead (Zones A, D) | Margaret Ogachi |  |
| Zone A Coordinator | Anne Obure |  |
| Zone B Coordinator | Hannah Gitonga |  |
| Zone C Coordinator | Tamara Ariba |  |
| Zone D Coordinator | Lorraine Muturi |  |
| Zone E Coordinator | Mercy Amuguni |  |
| Intern AV lead | — name 2–3 interns per the Event-Day Setup SOP |  |
| Command Post | Cizarina, Dr Muthoni, WG8 lead, Secretariat rep |  |

Cross-check the Zone Coordinator row against Section 20 before printing — the most recent SteerCo Action Log doesn't list Mercy Amuguni among confirmed WG2 members, so her Zone E assignment needs reconfirming, not just reprinting as-is.

## 20. Companion Documents & the WG2 App — What's Where Now

This Playbook is the plan. Three other documents and one live app now carry the day-of and role-specific detail that used to live only here — this section is the map of what's where, added 17 Aug 2026.

### 20.1 Companion Documents

| Document | What it covers | Supersedes/extends |
| --- | --- | --- |
| WG2_Event_Day_Setup_AV_Roles_SOP.docx | Room-readiness checklist, AV setup by mentor mode (In-person/Live virtual/Pre-recorded), AV-specific escalation, and the new-task list for closing the room/AV ownership gap this Playbook never assigned | New — no prior Playbook section covered this |
| WG2_Role_SOPs_All_Roles.docx | One section per WG2 role (Lead, Assistant Leads, Zone Coordinators, Cluster Leads, Sub-Leads, Mentors, Interns, Class Teacher/WG8 Liaison) — before/during/escalation/impact, grounded in the Section 18 schedule above, plus the full Escalation Ladder and a day-of RACI summary | Extends Section 12 (Cluster Leader SOP, which only ever covered one role) |
| WG2_Team_App_Setup_Guide.docx | How to install and use the WG2 App | Section 18.4 (Pre-Registration System) and Sections 19.2–19.6 |

### 20.2 The WG2 App — Live Features Worth Knowing About

Beyond registration, allocation, and check-in (Sections 18.4 and 19.2–19.6), the app now has three features that turn static planning numbers in this Playbook into a live, checkable status:

- Mentor Coverage Analysis (Reports tab) — a live, cluster-by-cluster read on which clusters have zero mentors, which are under-strength, and which are strongest, with the same recruitment-target math as Section 8.4 but computed from the actual current roster, not the static ~68/85–100 planning targets. Check this instead of assuming the Section 8.4 numbers still hold as recruitment progresses.

- Session/Shift Coverage (Dashboard, and the Intern My Day view) — flags any cluster that has some mentor coverage overall but a hole in one specific shift (Morning = Form 4's window; Afternoon = both Grade 10 waves), which the cluster-level view in Mentor Coverage Analysis can't catch on its own.

- Gap-filling mentor suggestions — for any flagged gap, the app suggests real candidates (from the Mentor Database's primary/secondary cluster fields and profession-fit keywords, confirmed Team members elsewhere, and — admin view only — pending applications), ranked by how directly they match, with contact details and the reason for each suggestion pre-filled into the recruitment task. This is what Section 9's secondary-cluster fix (above) actually feeds.

### 20.3 Companion Working Files

Task tracking is entirely in-app now — the team doesn't need a separate spreadsheet reference for it, and anyone who needs the full task list can pull it from the app directly. What's still useful as background reference: WG2_Cluster_Reference_2026.csv (full sub-field list, tiers, mergeable fallbacks, and what changed vs. 2023 — the master reference for the cluster reorganization) and WG2_Career_Day_2026_Draft_Programme.doc (printable programme card — note its round-by-round clock predates the Revision 3 schedule in Section 18.3 above; treat Section 18.3 as authoritative if the two disagree). The Cluster Allocation Matrix, Mentor Database, and student pre-registration data all now live in the WG2 App's own Google Sheet rather than as separate CSVs.

### 20.4 Flagged From the Latest SteerCo Action Log (Meeting 2/2026, 7 Aug 2026, approved 14 Aug)

Genuinely new or changed information from the most recent SteerCo minutes, for follow-up in both the app and this document set:

- New WG2 budget requirement. Action A02 requires WG2 to submit a budget to WG1 Finance — this Playbook has never tracked a WG2 budget line. Needs drafting and a home in the Task Tracker/app.

- Possible roster change — confirm before reprinting anything. The latest Action Log's WG2 members list no longer includes Mercy Amuguni, who Section 8.6 names as the draft Zone E Coordinator candidate. It adds Sharon Chelangat, Joyce Gatambia, and Mary Otieno Mugambi as confirmed Members instead. This may just be a different snapshot rather than a real change — confirm with Dr Muthoni/Cizarina before updating Section 8.6, the Staff Directory (Section 19.8), or the app's Team sheet.

- New "School Liaison: TBC" role named for WG2 in the latest Action Log, distinct from the Zone Coordinator/Cluster Lead structure this Playbook already documents. Needs a name and a place in Section 8's role table once confirmed.

- Old Dining Hall confirmed at 800–850 capacity for Labs (New Dining Hall at 1,300 for Plenary — WG4's concern). Already folded into Section 18.7 above; get WG8's written confirmation to close this out fully.

- "Finalise the proposed student tracking system for mentorship sessions" (Action A10) is already done — this is the WG2 App's QR check-in system. Good news, not a gap; worth reporting back to SteerCo as delivered rather than leaving it showing as open.

- Teachers and the Chaplain are to be added to the relevant cluster WhatsApp chats specifically (Action A09 in the new log), a more concrete version of the general "integrate teachers/Chaplain" duty already in Section 2.1.