Boma Career Day 2026

Event-Day Setup, AV & Roles SOP

Companion to the Coordination Playbook — assigns ownership for room readiness and AV setup, which the Playbook and the app's task list don't currently cover.

# 1. Why This Document Exists

A review of the Coordination Playbook (Sections 5, 6, 12, 14, 18) and the WG2 App's Event Day task list found seven existing day-of tasks — oversight, escalation, Command Post, feedback collection, attendance tracking, walk-in registration — but nothing assigning who checks that a room's screen works before a virtual or pre-recorded mentor's session, or who runs a general room-readiness check. This document fills that gap: a full roles roster, a setup timeline, room and AV checklists, a RACI table, an AV-specific escalation extension, and a ready list of new tasks to add to the app.

# 2. Full Roles Roster

Who's who on the day, building directly on the Playbook's existing escalation line (Mentor → Cluster Lead/Sub-Lead → Zone Coordinator → Assistant Lead → Lead → Secretariat), plus one recommended new role (Section 8).

| Role | Reports to | Day-of scope | Count |
| --- | --- | --- | --- |
| Lead (Dr Muthoni) | Secretariat | Whole event, roving oversight, final escalation point | 1 |
| Assistant Leads (Cizarina, Margaret) | Lead | Roving oversight of assigned zones (Cizarina: B+C+E; Margaret: A+D) | 2 |
| Zone Coordinators | Assistant Lead | Present & active across their zone's clusters, all shifts | 5 |
| Cluster Leads | Zone Coordinator | Facilitation, timekeeping, close-out per cluster | 23 (min. 1/cluster) |
| Cluster Sub-Leads | Cluster Lead | QR check-in, room setup confirmation, AV recheck, attendance tracking | 23 (min. 1/cluster) |
| Mentors | Cluster Lead | Deliver the mentorship session itself | 2–6/cluster by demand tier |
| Interns | Assigned Lead/Asst Lead | Delegable operational tasks — registration desk, recruitment follow-up, materials prep, AV sweep of all 23 rooms pre-doors and on-call for AV issues all day (Section 5) | Flexible; 2–3 tagged for AV |
| Class Teachers / WG8 Teacher Liaison | WG8 + Zone Coordinator | Class-level registration, confirmation, distribution, marshalling | Per class/stream |
| WG8 Teachers (marshals) | WG8 lead | Entrance staffing, movement marshalling, walk-in desk support | 1–2/zone |
| Secretariat rep | — | Command Post presence, programme-timing decisions | 1 |
| WG3 (Comms/photographer) | — | Mentor communications, one photographer per zone during mentorship | Per zone |
| WG4 (Plenary) | — | Owns Opening/Closing Plenary content AND its AV/sound — not WG2 | — |

# 3. Scope, and the Day's Timing

This document covers WG2's actual responsibility: room setup, AV, and the mentorship/lab sessions. The Opening and Closing Plenary are run entirely by WG4 — WG2 has no role in planning or staffing them, and they're intentionally not covered anywhere in this document.

Setup target: rooms fully ready — AV included — by 9:00am.

Mentorship schedule (the WG2 App's Revision 3, the schedule the app actually runs on): Form 4 mentorship 10:45am–12:15pm (optional round 4/exhibition swap to 12:40pm); Grade 10 Group A mentorship 1:00–2:30pm (swap to 2:55pm); Grade 10 Group B mentorship 2:30–4:00pm (its round4/exhibition swap runs earlier, 2:00–2:30pm). Every cohort finishes its last scheduled block by 4:00pm sharp. Rooms are reused sequentially through all three cohorts — never two cohorts mentoring in the same room at once.

# 4. Room Readiness Checklist (Every Room, Every Cluster)

General items, not AV-specific — owned by the Cluster Sub-Lead, confirmed by the Cluster Lead on arrival (extends the existing Cluster Leader SOP, Playbook Section 12, step 2: “confirm room setup”).

☐  Room/cluster signage visible from the corridor (ID + name)

☐  Seating arranged for the expected group size

☐  Discussion guide/materials present

☐  Water available

☐  Cluster Sub-Lead's phone charged, WG2 App installed and signed in, QR scanner tested

☐  Paper roster fallback printed and on hand (Playbook Section 19.4)

☐  AV checked — see Section 5 (only if this window's mentor is Live virtual or Pre-recorded)

# 5. AV Setup by Mentor Mode

KHS classrooms already have screens installed, so this is a connect-and-test job, not a procurement one. But a mentor's mode (In-person / Live virtual / Pre-recorded) is set per person, not per room — so the same room's AV need can change between the day's three windows if different mentors with different modes rotate through it. Check before every window, not just once in the morning.

| Mode | What's needed | Who checks / when |
| --- | --- | --- |
| In-person | Nothing — no AV involved | — |
| Live virtual | Screen powered on, correct input selected; mentor's own device (or a shared one) connected; Wi-Fi/data confirmed; video call link tested and joined a few minutes early; volume checked | Cluster Sub-Lead, before each window this mentor is scheduled — escalate to the Intern AV team if it fails |
| Pre-recorded | Screen on, correct input selected; video file loaded — saved locally on the device, not just a streaming link, so a Wi-Fi drop doesn't stop playback; volume checked; someone identified to run play/pause | Cluster Sub-Lead, before each window this mentor is scheduled — escalate to the Intern AV team if it fails |

# 6. Setup & AV RACI

R = Responsible · A = Accountable · C = Consulted · I = Informed — mirrors the Coordination Playbook's Section 6 format.

| Task | Lead | Asst Leads | Zone Coord | Cluster Lead/Sub-Lead | Interns |
| --- | --- | --- | --- | --- | --- |
| Pre-doors AV sweep (all 23 rooms) | I | I | C | C | R/A |
| Between-window AV recheck | I | I | I | R/A | C |
| General room readiness (signage/seating/water) | I | I | C | R/A | C |
| AV failure mid-session | I | I | C | R | A |

# 7. Escalation — AV-Specific

Extends the Playbook's Section 14 Escalation & Risk Log with AV-specific rows.

| Risk | Response | Owner |
| --- | --- | --- |
| Screen/device fails mid-session | Sub-Lead switches to a verbal/discussion-only format for the rest of that window; flags the Intern AV team for a fix before the next window | Cluster Sub-Lead |
| Wi-Fi drops during a Live virtual session | Try the mentor's own hotspot/data if available; otherwise the mentor calls in by phone, or the session pauses and it's noted in the close-out report | Cluster Sub-Lead |
| Pre-recorded video won't play | Use the locally-saved backup copy; if that also fails, run the session as a facilitated discussion using the printed discussion guide | Cluster Sub-Lead |
| Multiple rooms report AV issues at once | Intern AV team triages by cluster demand (oversubscribed clusters first, per Capacity & Coverage); escalate to Zone Coordinator if unresolved before the next window | Interns + Zone Coordinator |

# 8. New Tasks — Add These via the App

These aren't pre-loaded into the app automatically: the Tasks sheet already has live data, and new task IDs are generated by the app itself when you use its own “+ Add Task” button (Tasks tab) — so adding them there, rather than pasting rows directly into the Sheet, avoids any chance of an ID clash. No file upload or redeploy needed for this part; just add each row below through the app.

| Task | Phase | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| Name 2–3 Interns for AV duty (roving across all 23 rooms) | Week 3 - Confirm and Rehearse | Cizarina | 22-Aug-26 | Not a new Team Access role — just an assignment within existing Intern tasks |
| Confirm every Live-virtual and Pre-recorded mentor's link/video file is ready and tested | Week 3 - Confirm and Rehearse | Interns | 27-Aug-26 | Pre-recorded videos should be saved locally on the room's device, not just a streaming link |
| Pre-doors AV sweep of all 23 rooms — screen on, correct input, sound check | Event Day | Interns (AV duty) | 29-Aug-26 | Target: complete before 9:00am room-ready deadline (Section 3) |
| Between-window AV recheck at every shift changeover (F4 → G10A → G10B) | Event Day | Cluster Sub-Leads | 29-Aug-26 | A room's AV need can change if different mentors with different modes rotate through it — escalate if broken |

# 9. Out of Scope

- Opening and Closing Plenary — content, staging, and AV/sound are entirely WG4's. Not a WG2 task, not tracked here.

- Sourcing or procuring screens/TVs — KHS classrooms already have them installed; this document only covers connecting and testing.