Boma Career Day 2026

WG2 Role SOPs — Everyone's What, When, Where

Companion to the Coordination Playbook and the Event-Day Setup, AV & Roles SOP. One section per role: what they do, when, where, and what breaks if the role isn't staffed.

# 1. How to Read This Document

Every WG2 role on Career Day gets its own section below, in the same shape: Before the Day, Event Day (what/when/where), If Something Goes Wrong, and Impact if the role is missing. The goal is that everyone — Lead down to Intern — can read their own section in under two minutes and know exactly what's expected, without needing to cross-reference the full Coordination Playbook on the day itself.

This document does not replace the Coordination Playbook (the source for most of the facts below — Sections 5, 6, 8, 12, 14, 18, 19) or the Event-Day Setup, AV & Roles SOP (room/AV readiness detail). It sits alongside them as the day-of quick reference, organised by person instead of by topic.

# 2. Scope — What WG2 Actually Runs on the Day

WG2 owns the mentorship rounds and the lab sessions students move through across the day. The Opening and Closing Plenary belong entirely to WG4 — content, staging, and AV/sound — and are intentionally not covered anywhere in this document; no WG2 role has a Plenary duty.

Within the day, WG2's roles split into two kinds of duty: the cluster-room roles (Cluster Lead, Sub-Lead, Mentor) are only actively “on” during their cluster's mentorship windows — the app's shift model (Morning = Form 4's window, Afternoon = both Grade 10 waves) is what determines which windows a given person covers. The oversight roles (Lead, Assistant Leads, Zone Coordinators) are effectively on duty the full day, since their zones/clusters are in a mentorship window at some point in all three slots.

Note: Lab sessions (Lab1/Lab2) run in separate lab space with KICD/KUCCPS experts, coordinated with WG8 (Playbook Sections 7.5 and 19.5) — Cluster Leads, Sub-Leads and Mentors do not staff the lab rooms themselves. If that staffing model has changed since the Playbook was written, flag it to Dr Muthoni so this document can be corrected rather than left silently wrong.

# 3. Event Day at a Glance — All Three Cohorts

Source: the WG2 App's own schedule data (15 Aug 2026, Revision 3) — the schedule the app actually runs on, not the Playbook's earlier Section 18 draft. Setup target: rooms and AV fully ready by 9:00am, before any cohort's first block. Every cohort finishes its last scheduled block by 4:00pm sharp.

Form 4 (450 students)

| Time | Block | WG2 role |
| --- | --- | --- |
| 10:45–11:15 | Mentorship Round 1 | Active — Cluster Lead, Sub-Lead, Mentors |
| 11:15–11:45 | Mentorship Round 2 | Active |
| 11:45–12:15 | Mentorship Round 3 | Active |
| 12:15–12:40 | Round 4 (pre-arranged extra) OR Exhibition 1 | Active only for students/mentors with a pre-arranged Round 4 — otherwise not WG2 |
| 12:40–13:00 | Lunch | Not WG2 |
| 13:00–14:00 | Lab 1 | Not WG2 — KICD/KUCCPS + WG8 |
| 14:00–15:00 | Exhibition 2 (compulsory) | Not WG2 |
| 15:00–16:00 | Lab 2 | Not WG2 — KICD/KUCCPS + WG8 |

Grade 10 — Group A (398 students)

| Time | Block | WG2 role |
| --- | --- | --- |
| 10:45–11:45 | Lab 1 | Not WG2 |
| 11:45–12:15 | Exhibition 1 (compulsory) | Not WG2 |
| 12:15–13:00 | Lunch | Not WG2 |
| 13:00–13:30 | Mentorship Round 1 | Active — Cluster Lead, Sub-Lead, Mentors |
| 13:30–14:00 | Mentorship Round 2 | Active |
| 14:00–14:30 | Mentorship Round 3 | Active |
| 14:30–15:00 | Round 4 (pre-arranged extra) OR Exhibition 2 | Active only for pre-arranged Round 4 — otherwise not WG2 |
| 15:00–16:00 | Lab 2 | Not WG2 |

Grade 10 — Group B (398 students)

| Time | Block | WG2 role |
| --- | --- | --- |
| 10:45–11:45 | Lab 1 | Not WG2 |
| 11:45–12:15 | Exhibition 1 (compulsory) | Not WG2 |
| 12:15–13:00 | Lunch | Not WG2 |
| 13:00–14:00 | Lab 2 | Not WG2 |
| 14:00–14:30 | Round 4 (pre-arranged extra) OR Exhibition 2 | Active only for pre-arranged Round 4 — otherwise not WG2 |
| 14:30–15:00 | Mentorship Round 1 | Active — Cluster Lead, Sub-Lead, Mentors |
| 15:00–15:30 | Mentorship Round 2 | Active |
| 15:30–16:00 | Mentorship Round 3 | Active |

Note: Rooms are reused sequentially through all three cohorts — never two cohorts mentoring in the same room at once. A cluster's room hosts Form 4 first (10:45–12:15), then Grade 10 Group A (13:00–14:30), then Grade 10 Group B (14:30–16:00).

# 4. Lead — Dr Muthoni Mugambi

Final decision-maker and escalation point for all of WG2; owns the mentorship strategy and represents WG2 to Secretariat and SteerCo.

Reports to: Secretariat     Count on the day: 1

Before the day

- Signs off the cluster structure, zone assignments, and Zone Coordinator appointments (Playbook Sections 7–8).

- Submits WG2's mentorship-time requirement to Secretariat/WG4 (Action A20).

- Chairs the Mentor Briefing Session (Playbook Section 13).

- Runs the final check-in call with all Cluster Leads and Zone Coordinators (target 27 Aug).

Event day — what, when, where

- Roving oversight across all zones — not tied to one, unlike the Assistant Leads' zone split.

- Based at the Command Post (Playbook Section 18.7) alongside a WG8 lead and Secretariat rep, reachable by phone/WhatsApp throughout.

- Final escalation point when a Zone Coordinator's issue can't be resolved by Cizarina or Margaret directly.

If something goes wrong

- Whole-zone problems (multiple issues at once) escalate here from an Assistant Lead — see Section 12 for the full ladder.

- Any decision that affects the programme's timing (e.g. extending a slot) needs sign-off here, then Secretariat.

Impact if this role is missing or under-resourced

No final decision-maker for cross-zone or programme-timing issues — escalations stall at the Assistant Lead level with nobody empowered to make the call, or every decision gets routed to Secretariat directly, defeating the point of WG2's own escalation ladder.

# 5. Assistant Leads — Cizarina Nasirumbi & Margaret Ogachi

Roving oversight of an assigned set of zones — the layer between Zone Coordinators and the Lead. A deliberately uneven split by cluster count, grouped by domain adjacency (Playbook Section 8.2).

Reports to: Lead (Dr Muthoni)     Count on the day: 2 — Cizarina: Zones B, C, E (15 clusters); Margaret: Zones A, D (8 clusters)

Before the day

- Own the roster, workplan, Cluster Allocation Matrix, Mentor Handbook, and every SOP in this document set (Playbook RACI, Section 6).

- Own the WG2 App rollout and data quality — Mentor Database, Session Coverage, task assignment.

- Confirm each Zone Coordinator's fit against interest/network during Phase 0 (Section 8.6).

Event day — what, when, where

- Present at the 9:00am room-ready check, then roving their assigned zones throughout all three mentorship windows.

- Reachable by phone/WhatsApp at all times — the live escalation contact Zone Coordinators call first (Playbook Event Day table).

- Given the imbalance (15 vs 8 clusters), Cizarina's zones get first call on floater/deputy Zone Coordinator support if one zone is short-handed.

If something goes wrong

- Mentor no-show or overcrowding a Zone Coordinator can't resolve alone — escalates here.

- Anything genuinely whole-zone or affecting multiple zones — escalates onward to Dr Muthoni.

Impact if this role is missing or under-resourced

Zone Coordinators have no one to escalate zone-wide issues to except each other or Dr Muthoni directly — bypassing the intended structure and overloading the Lead with problems the Assistant Lead layer exists to absorb.

# 6. Zone Coordinators

WG2's single point of contact for every cluster in their zone — turns “3 people overseeing 23 rooms” into “3 people overseeing 5 coordinators” (Playbook Section 8.1).

Reports to: Assigned Assistant Lead     Count on the day: 5 — one per zone (A–E)

Before the day

- Confirm a Cluster Lead and Sub-Lead for every cluster in the zone (Action A17) — this is the single most important pre-event WG2 task.

- Join the final check-in call with Dr Muthoni.

- Know every cluster room's location and every mentor's shift assignment in the zone.

Event day — what, when, where

- Present and active across the zone's clusters through all three mentorship windows — a zone's rooms are busy during whichever cohort is currently in mentorship, so Zone Coordinators are effectively on duty from before 9:00am through 4:00pm.

- First responder for a mentor no-show: texts a backup mentor from the app's suggested-candidates list (Session Coverage — see the WG2 App's Dashboard) while the Sub-Lead absorbs the group informally.

- Redirects overflow from an overcrowded cluster to the nearest same-theme cluster or a holding area.

- Coordinates any room change with WG8's on-site contact and updates signage.

If something goes wrong

- Mentor no-show — texts a backup mentor; if none responds in time, escalates to the Assistant Lead.

- Overcrowding — redirects overflow; if the whole zone is affected, escalates to the Assistant Lead.

- Anything spanning multiple zones at once — escalates directly to Cizarina/Dr Muthoni (Playbook Section 14).

Impact if this role is missing or under-resourced

No first-line responder for no-shows or overcrowding in that zone — issues either go unresolved through a mentorship round, or get escalated straight to the Assistant Lead, defeating the point of the zone layer and overloading one person with 15–23 rooms' worth of issues.

# 7. Cluster Leads

Owns facilitation and timekeeping for one cluster room — the Playbook's existing Cluster Leader SOP (Section 12), scoped here to the exact mentorship windows above.

Reports to: Zone Coordinator     Count on the day: 23 minimum — 1 per cluster

Before the day

- Confirm attendance and shift (Morning = Form 4 only; Afternoon = both Grade 10 waves; Either/Both = all three windows).

- Review the discussion guide for the cluster.

- Know the room and every scheduled time slot for the shift you've committed to.

- Know your Zone Coordinator's contact.

- Attend the Mentor Briefing Session.

Event day — what, when, where

- Arrive by the 9:00am room-ready target for your shift's first window.

- Check in with the Zone Coordinator on arrival; confirm mentor headcount and room setup (Event-Day Setup SOP, Section 4).

- Facilitation: keep every round to time (25 min + 5 min changeover), make sure every student gets to speak or ask a question, steer toward practical guidance rather than only career anecdotes.

- Timekeeping: hard stop at each round's scheduled end — protects the next round or the next cohort's rotation.

- Close-out: distribute the mentor feedback form/QR before mentors leave; report headcount to the Zone Coordinator — once per cohort's mentorship window, since the same room hosts all three cohorts in sequence.

If something goes wrong

- A mentor doesn't show, or the room is overcrowded — contact the Zone Coordinator immediately; don't try to solve it silently.

Impact if this role is missing or under-resourced

No one keeping rounds on time or ensuring every student is engaged — rounds run long and cascade delays into the next round or the next cohort's slot; no headcount reported means Command Post loses visibility into whether the room actually ran.

# 8. Cluster Sub-Leads

Handles QR check-in, room/AV readiness confirmation, and attendance tracking — deliberately not the mentor, so the mentor stays free to mentor (Playbook Section 19.3).

Reports to: Cluster Lead (functionally), Zone Coordinator (structurally)     Count on the day: 23 minimum — 1 per cluster

Before the day

- Same briefing/discussion-guide review as the Cluster Lead.

- Install the WG2 App, sign in, and test the QR scanner before the day.

- Know the room's AV mode requirements for each scheduled mentor (In-person / Live virtual / Pre-recorded — Event-Day Setup SOP, Section 5).

Event day — what, when, where

- Before each window: confirm the room-readiness checklist (Event-Day Setup SOP, Section 4) and re-check AV if this window's mentor is Live virtual or Pre-recorded — a room's AV need can change between windows if different mentors rotate through.

- At the start of each round: check in incoming students via the WG2 App's Check-In → Scan QR tab (or Search if a card is damaged or the camera's unavailable).

- Throughout: logs attendance, which feeds the Dashboard's Live Today panel for Command Post visibility.

- If a mentor doesn't show: absorbs the group informally as a stopgap until the Zone Coordinator arranges a backup.

If something goes wrong

- AV failure mid-session — escalate to the Intern AV team (Event-Day Setup SOP, Section 7).

- Mentor no-show — absorb the group, notify the Cluster Lead and Zone Coordinator immediately.

Impact if this role is missing or under-resourced

No one dedicated to check-in — either the mentor stops mentoring to handle it (exactly what this role exists to prevent), or check-in doesn't happen at all and Command Post has no live read on which rooms are running, empty, or overcrowded.

# 9. Mentors

Delivers the actual mentorship conversation — the core purpose of the day, and the role every other WG2 role exists to support.

Reports to: Cluster Lead     Count on the day: 2–6 per cluster, by demand tier (Playbook Section 8.4)

Before the day

- Confirm attendance and shift (Morning / Afternoon / Either-Both).

- Attend the Mentor Briefing Session; review the discussion guide.

- Confirm delivery mode (In-person / Live virtual / Pre-recorded); if Live virtual or Pre-recorded, confirm tech readiness with the Cluster Sub-Lead in advance — not for the first time on the day.

Event day — what, when, where

- Arrive per shift: Morning shift covers Form 4's window only (10:45–12:15); Afternoon shift covers both Grade 10 waves back-to-back (13:00–16:00); Either/Both covers the full day.

- Deliver each 25-minute round to the room; hard-stop at the round's end so the next round or rotation isn't delayed.

- Complete the mentor feedback form/QR before leaving the venue (Playbook Section 11).

If something goes wrong

- Anything blocking the session (AV, overcrowding, a student issue) — flag to the Cluster Sub-Lead or Cluster Lead immediately rather than working around it solo.

Impact if this role is missing or under-resourced

A no-show mentor is the single gap the WG2 App's Session/Shift Coverage and mentor-suggestion features exist to catch before the day — on the day itself, the Sub-Lead absorbs the group as a stopgap and the Zone Coordinator texts a backup mentor from the app's suggested list, but a student group genuinely goes without that round's mentorship until one of those lands.

# 10. Interns

WG2's operational engine — registration, recruitment follow-up, materials prep, and (folded in, not a separate role) AV sweep and on-call support.

Reports to: Assigned Lead or Assistant Lead     Count on the day: Flexible; 2–3 specifically tagged for AV duty

Before the day

- Stand up and maintain the Mentor Database; action every coverage gap the app's Dashboard and My Day panel surface (Session Coverage cards, suggested-mentor list).

- Send final logistics to every confirmed mentor (venue, time, room, shift — target 24 Aug).

- Prepare on-the-day materials: signage, attendance sheets, discussion guides, feedback QR codes (target 27 Aug).

- Source and order wristbands (3 colours, ~1,250 units with buffer).

- Test the QR scanning process end-to-end before the day.

- Name 2–3 interns specifically for AV duty, roving across all 23 rooms (Event-Day Setup SOP, Section 8).

Event day — what, when, where

- Pre-doors AV sweep of all 23 rooms before the 9:00am room-ready target — screen on, correct input, sound check.

- Staff the registration/walk-in desk alongside class teachers.

- On-call for AV issues all day — triage by cluster demand if multiple rooms report issues at once, escalate to the Zone Coordinator if unresolved before the next window.

- Compile mentor feedback results and send thank-you messages post-event.

If something goes wrong

- Multiple AV issues at once — triage by cluster demand tier; escalate to the Zone Coordinator if still unresolved before the next window.

Impact if this role is missing or under-resourced

Coverage gaps go unfilled because nobody actions the app's suggested-mentor list before the day; AV issues have no on-call responder; walk-in students have no desk to register at.

# 11. Class Teachers / WG8 Teacher Liaison

Not a WG2 role — WG2's essential day-of partner for anything that touches students directly: registration, confirmation, distribution, and movement (Playbook Section 19.5, Action A32).

Reports to: WG8 lead (coordinates with WG2 Zone Coordinators, not managed by them)     Count on the day: Per class/stream, plus 1–2 per zone for entrance/movement marshalling on the day

Before the day

- Run pre-registration as a supervised in-class session (one period, phones or a projected screen) — far more reliable than an unsupervised link.

- Once allocation runs, open the WG2 App's Schedule → My Class view (auto-filtered to their own stream) and project it in class so students see their confirmed placement digitally before anything is printed.

- Distribute wristbands and printed QR Itinerary Cards in class with a short (10-minute) orientation: wristband colours, how to use the Digital Day Guide if a card is lost.

Event day — what, when, where

- Provide 1–2 teachers per zone as additional marshals alongside WG2 Zone Coordinators, focused on corridor/junction points, not just zone entrances.

- Staff the walk-in desk jointly with a WG2 intern — teachers can verify a student's identity/class instantly.

- Help move their own form/stream between mentorship and lab slots at every transition point.

If something goes wrong

- A student in the wrong place, a lost card, or confusion at a transition — handled directly, or pointed to the Digital Day Guide; escalate to the nearest Zone Coordinator only if it's a room/schedule problem rather than an individual student issue.

Impact if this role is missing or under-resourced

Pre-registration data becomes unreliable or incomplete without supervised in-class collection (the Playbook is explicit that an unsupervised link is worse); without teacher marshals, WG2's Zone Coordinators alone can't move 1,246 students through transitions cleanly.

# 12. Escalation Ladder — Full Chain

Mirrors the Coordination Playbook's Section 8.2 reporting line and Section 14 Escalation & Risk Log, in one place for quick reference.

| From | First contact | Then, if unresolved |
| --- | --- | --- |
| Mentor | Cluster Lead / Sub-Lead | Zone Coordinator |
| Cluster Lead / Sub-Lead | Zone Coordinator | Assistant Lead (Cizarina or Margaret, per zone) |
| Zone Coordinator | Assistant Lead | Lead (Dr Muthoni) |
| Assistant Lead | Lead | Secretariat |
| Class Teacher / WG8 Liaison | Nearest Zone Coordinator (room/schedule issues only) | WG8 lead (student-specific issues) |
| Intern (AV) | Zone Coordinator (if unresolved before next window) | Assistant Lead |

# 13. RACI Summary — Day-of Responsibilities

R = Responsible · A = Accountable · C = Consulted · I = Informed — mirrors the Playbook's Section 6 format, scoped to event-day execution.

| Task | Lead | Asst Leads | Zone Coord | Cluster Lead/Sub-Lead | Mentors | Interns |
| --- | --- | --- | --- | --- | --- | --- |
| Room & AV readiness by 9:00am | I | I | C | R/A | — | R |
| Facilitation & timekeeping per round | I | I | I | R/A | R | — |
| Student check-in / attendance | I | I | I | R/A | — | — |
| Mentor no-show response | I | C | R/A | R | — | C |
| Overcrowding / room change | I | C | R/A | C | — | — |
| Mentor feedback collection | I | I | I | R | R | A |
| Coverage-gap recruitment (pre-event) | I | A | C | — | — | R |

# 14. Out of Scope

- Opening and Closing Plenary — content, staging, and AV/sound are entirely WG4's. No WG2 role has a Plenary duty.

- Lab session facilitation — run by KICD/KUCCPS experts, coordinated with WG8. WG2's cluster-room roles do not staff lab rooms.

- Catering/lunch logistics — provided by the school; not a WG2 dependency.

# 15. Companion Documents

- WG2_Career_Day_2026_Coordination_Playbook — the full plan (structure, cluster reorganisation, mentor database, student grouping, feedback tool, success metrics).

- WG2_Event_Day_Setup_AV_Roles_SOP — room-readiness and AV checklists, AV-specific escalation, and the new-task list for room setup.

- WG2_Team_App_Setup_Guide — how to install and use the WG2 App (registration, allocation, check-in, dashboards).

- WG2_Cluster_Reference_2026.csv, WG2_Mentor_Database.csv, WG2_Cluster_Allocation_Matrix.csv — live working data behind the roles above.